## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE | [6 empty] | INSTUTUTE & DEPARTMENT NAME | [6 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(Information Technology)
PROJECT GUIDE | [6 empty] | DATE | [6 empty] | 2022-03-25
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [44 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Soham Bolla , Sakshi ahire ,Sakhsi Gaikwad | 2023-01-13 | 2023-01-18 | 2 | 100% | bar: WEEK 1 M to WEEK 2 F
1.2 | Identifying the functionalities of the Mini Project | Soham Bolla | 2023-01-20 | 2023-01-26 | 2 | 100% | bar: WEEK 3 M to WEEK 5 F
1.3 | Discussing the ML Algorithm. | Sakshi Ahire | 2023-01-29 | 2023-02-03 | 2 | 100% | bar: WEEK 5 M to WEEK 6 F
1.4 | Designing the Graphical User Interface(GUI) | Sakshi Gaikwad | 2023-02-04 | 2023-02-10 | 2 | 100% | bar: WEEK 7 M to WEEK 8 F
1.5 | Review 1 Presentations | Sakshi Ahire | 2023-02-17 | 2023-02-17 | 1 | 100% | bar: WEEK 9 M to WEEK 9 F
2 | Project Design and Implementation
2.1 | Detail ML Algorithm implemnt | Soham Bolla | 2023-02-20 | 2023-02-28 | 1 | 100% | bar: WEEK 10 M to WEEK 10 F
2.2 | Integration of GUI with ML Algorithm code | Sakshi Gaikwad | 2023-03-03 | 2023-03-10 | 1 | 100% | bar: WEEK 11 M to WEEK 12 F
2.3 | Report Writing | Sakshi Ahire | 2023-03-14 | 2023-03-21 | 1 | 100%
2.4 | Review 2 Presentations | Soham Bolla | 2023-03-13 | 2023-03-13 | 2 | 100% | bar: WEEK 12 M to WEEK 14 F